## Current
ACTIVE PROCUREMENTS (As at 24FEB2020)
RFI / RFP Issuance Forecast Date | RFP Response Forecast Date | Contract Award Forecast Date | Procurement Stage | Program | Scope of Work | Contract Type | Commercial Lead
2019-06-01 | 28/06/2019 | 2020-03-10 | Proposal Review | MCR Unit 3 | FCFR - Feeder Pipe | Materials | Dave Porcellato
2019-06-01 | 26/07/2019 | 2020-04-10 | Evaluation | MCR Unit 3 | Construction Services - Retube Waste Containers | Materials | Dave Porcellato
2019-12-12 | 2020-01-08 | 2020-03-04 | RFP Response | MCR Unit 3 | F & I- Construction Contract Award-Parking Lot Extension | Services | Jeremy Beaty
2019-11-27 | 2020-01-06 | 2020-03-31 | RFP Preparation | MCR Unit 3 | BOP-Detail Design Contract PSUI - In-Core Fission Chamber for New Core SUI-Electrical | Services | Dave Porcellato
2020-03-27 | 2020-04-09 | 2020-08-07 | RFP Preparation | Outages | Circumferential Wet Scrape Tool ("CWEST") Inspection Execution, Maintenance and Testing | Services | Holly Goodings
2020-04-28 | 2020-04-09 | 2020-08-07 | RFP Preparation | Maintenance | Eddy Current Inspection Program Multi-Year Preferred Supplier Agreement | Services | Holly Goodings
2020-03-30 | 2020-05-11 | 2020-08-15 | RFP Preparation | Materials | Health and Safety Multi-Year Preferred Supplier Agreement | Services | Holly Goodings
2020-01-17 | 2020-02-14 | 2020-03-01 | RFP Preparation | MCR | U3 MCR FI EAST END COMPLEX ENGINEERING | Services | Jeremy Beaty
2020-02-28 | 2020-03-27 | 2020-04-28 | RFP Preparation | MCR Unit 3 | BOP - Detail Design Contract - Breathing Air System Modifications | Services | Dave Porcellato
2020-02-10 | 2020-03-09 | 2020-07-07 | RFQ Preparation | MCR Unit 3 | BOP-Elastomeric Seals for Bulkheads - Bulkheads | Materials | Dave Porcellato
5/15/2020 | 6/1/2020 | 6/25/2020 | RFP Preparation | MCR Unit 3 | Construction Services-Execution and Materials Procurement (No Eng Required Work) | Services | Dave Porcellato
1/23/2020 | 2/4/2020 | 3/19/2020 | RFP Response | MCR Unit 3 | BOP-Detail Design Contract - PHT Drain and Dry | Services | Dave Porcellato
1/23/2020 | 2020-02-13 | 3/24/2020 | RFP Response | MCR Unit 3 | BOP-Detail Design Contract - Moderator Drain and Dry | Services | Dave Porcellato
1/23/2020 | 2020-02-14 | 2020-03-25 | RFP Response | MCR Unit 3 | BOP-Detail Design Contract - System Layup | Services | Dave Porcellato
2020-04-16 | 13/07/2020 | 2020-12-17 | RFP Preparation | MCR Unit 3 | SGR-Award of Contract for Inspection and Refurbishment of Steam Drum | Services | Dave Porcellato
2020-01-29 | 2020-02-20 | 2020-05-04 | Evaluation | MCR Unit 3 | SGR-Detailed Engineering for SDS1 & SDS2 Relay Installation | Services | Dave Porcellato
2020-02-12 | 2020-03-13 | 2020-04-30 | RFP Prepartation | Centre of Site | Installation of Fibre and new IT panels | Services | Jeremy Beaty
2019-09-25 | 2019-11-15 | N/A | Evaluation | Engineering | RFI - Emergency Water Supply (EWS) Piping | Services | Connie O'Malley
2020-02-14 | 2020-03-09 | 2020-04-20 | RFQ Issued | MCR Unit 3 | Channel Closure Plugs | Materials | Lisa Keown
2020-04-01 | 2020-06-01 | 2020-07-13 | RFP Prepartation | MCR Unit 3 | Weld Wire | Materials | Lisa Keown
Legend
WM - Work Management |  | AM - Asset Management
LILO - Lead In Lead Out |  | SGR-Steam Generator Replacement
F&I - Facilities & Infrastructure |  | PMC - Project Management and Construction
DTRT - Detube Retube |  | FCFR - Feeder Channel Feeder Replacement |  |  |  |  | (continued on 2nd page)
RFI - Request for Information |  | MCR - Major Component Replacement
RFP - Request for Proposal |  | BOP - Balance of Plant
Formulas:
RFP Response Forecast Date = [RFI / RFP Issuance Forecast Date]+28

## Coming Soon
COMING SOON (As at 24FEB2020)
Forecast Date | Program | Scope of Work | Contract Type | Commercial Lead
Q1 2020 | Maintenance | FH Brakes and Clutches | Material | Peggy Coffey
Q1 2020 | AM | Enterprise Wide Phase 3 Guelph Swing Check Valve RFP | Materials | Lori Trowbridge
Q1 2020 | Site Services | Sewage Processing Plant Controls Upgrade | Services | Jeremy Beaty
Q1 2020 | Site Services | RFI - Bruce A New Demineralized Water Treatment Plant | Services | Jeremy Beaty
Q1 2020 | Engineering | RFI - Heat Exchanger Cleaning and Measurement Technology Updates | Services | Grant Ross
Q2 2020 | AM | Enterprise Cable and Wire Supply | Material | Tony Swift
Q2 2020 | Maintenance | Fuel Handling D20 Valve Standarization | Material | Peggy Coffey
Q2 2020 | Materials | Maintenance, Repair and Operating (MRO) Consumables, Multi- Year Preferred Supplier Agreement | Materials | Holly Goodings
Q2 2020 | AM | Enterprise Wide Phase 4 Valve RFP | Materials | Lori Trowbridge
Q2 2020 | AM | PHT Motor Decontamination/Scrap | Services | Carly Bragg
Q2 2020 | AM | Fixed Area Gamma Monitor (FAGM) | Material | Tony Swift
Q3 2020 | MCR Unit 3 | Tooling Refurb-Tooling Materials (Including Spares Replenishment) | Materials | Dave Porcellato
Q3 2020 | MCR Unit 3 | Carbon Steel to Carbon Steel Weld Wire | Materials | Dave Porcellato
Q3 2020 | AM | Small Motors | Materials | Carly Bragg
Q3 2020 | AM | Small Pumps | Materials | Carly Bragg
Q3 2020 | AM | High Voltage Preferred Supplier Agreement | Services | Julie Ernewein
Q3 2020 | Engineering | Project Controls (Managed Task) | Services | Grant Ross
Q3 2020 | Site Services | Douglas Point Road Resurfacing | Services | Jeremy Beaty
Q4 2020 | MCR Unit 3 | Channel Closure Plugs | Materials | Dave Porcellato
Q4 2020 | MCR Unit 3 | Feeder Cabinets | Materials | Dave Porcellato
Q4 2020 | MCR Unit 3 | Construction Electrical Power Supplies- Execution - Installation - Contract Award | Services | Dave Porcellato
Q4 2020 | MCR Unit 3 | Resistant Temperature Detectors | Materials | Dave Porcellato
Q4 2020 | MCR Unit 3 | Thermowell Nozzels and DN Adapters | Materials | Dave Porcellato
Q4 2020 | MCR Unit 3 | Feeder Supports | Materials | Dave Porcellato
Q4 2020 | MCR Unit 3 | Crane Animation Contract Award | Services | Dave Porcellato
Q4 2020 | MCR Unit 3 | SGR-Award of Contract for Crane Pad Construction | Services | Dave Porcellato
Q4 2020 | MCR Unit 3 | Construction Services-Materials Procurement-Electrical Power Supplies | Materials | Dave Porcellato
Q4 2020 | MCR Unit 3 | SGR-Award of Execution Contract for Construction Phase | Services | Dave Porcellato
Q2 2021 | MCR Unit 3 | BOP-Material Procurement | Materials | Dave Porcellato
Q3 2021 | MCR Unit 3 | Feeder Instrumentation Supports | Materials | Dave Porcellato
Q4 2021 | MCR Unit 3 | SGR-Award of Contract for SDS1 & SDS2 Relay Installation | Service | Dave Porcellato